## Product Backlog
User stories | Priority | Effort (Hour) | Owner | Status | Definitions of Done | Sprint | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
As a customer, I want to be able to log in to use the booking system | 1 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As a worker, I want to be able to log in so I can view the customers who have a booking with me | 1 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to be able to log in so I can view the dashboard to monitor the bookings of the day | 1 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As a customer, I want to sign up to view the services of the application | 1 | 10 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to sign up to provide my services to cusstomers | 1 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As a customer, I want to find information on the contact us page so I can find admin/worker's contact | 2 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to list my contact details on the contact us page so I can publish my contact to customers | 2 | 8 | WInston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As a worker, I want to list my contact details on the contact us page so I can publish my contact to customers | 2 | 8 | Winston | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to add new worker so all new workers are accounted for | 1 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to edit worker information so that any details can be changed/removed when needed | 1 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment | 1
As an admin, I want to add working times/dates for the next month so that workers know when they are working | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As an admin, I want to edit working times/dates for the next month so that any emergencies changes can be made when needed | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As an admin, I want to see past bookings so that there is a log of past work available when needed | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As an admin, I want past bookings to be sorted by date so that it is easier to look for a speficic booking | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As an admin, I want to see all worker availability for the next seven days so that workers' availability is known for working purpose | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to check for available days/times so that I know when I can book a service | 3 | 8 | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to check for services so that I know what services I can book | 3 |  | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to check the worker providing the service so that I know who it is that is working on my booking | 3 |  | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to book a specific worker, day and service so that I can choose the person I want, when I want, for what I need them to do | 3 |  | Rodrigo | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a worker, I want to view my profile page so that I can see my assigned working hours | 3 |  | David | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a worker, I want to view my profile so that I can see the days on which I work and when I have appointments | 3 | 8 | David | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to cancel my booking 48 hours before my appointment so that I don't have to pay for a booking I cannot attend | 3 | 8 | David | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As a customer, I want to view the history of my booking so that I can check how often do I use the services | 3 | 8 | Nam | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment
As an admin, I want to view worker's assigned working hour and booked services so that I can assure that the roster is correctly set up | 3 | 8 | Nam | Not yet started | Code is uploaded to github, Code passes use case tests, Code passes acceptance tests, Code is peer reviewed, Code is documented, Code is tested in production environment

## Sprint 1 Backlog
User stories | Task | Priority | Effort (Hour) | Assigned | Status | Sprint | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
As a customer, I want to be able to log in to use the booking system | Design log in UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert log in UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create log in API back-end | 2 | 4 | Nam | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | Nam | Not yet started | 1
As a worker, I want to be able to log in so I can view the customers who have a booking with me | Design log in UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert log in UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create log in API back-end | 2 | 4 | Nam | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | Nam | Not yet started | 1
As an admin, I want to be able to log in so I can view the dashboard to monitor the bookings of the day | Design log in UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert log in UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create log in API back-end | 2 | 4 | Nam | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | Nam | Not yet started | 1
As a customer, I want to sign up to view the services of the application | Design sign up UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert sign up UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Set up cloud database | 1 | 2 | Nam | Not yet started | 1
| Create sign up API back-end | 2 | 4 | Nam | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | Nam | Not yet started | 1
As an admin, I want to sign up to provide my services to customers | Design sign up UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert sign up UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create sign up API back-end | 2 | 4 | Nam | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | Nam | Not yet started | 1
As a customer, I want to find information on the contact us page so I can find admin/worker's contact | Design contact info for customer UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert contact info for customer UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create contact info for customer API back-end | 2 | 4 | David | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | David | Not yet started | 1
As an admin, I want to list my contact details on the contact us page so I can publish my contact to customers | Design contact info for admin UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert contact info for admin UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create contact info for admin API back-end | 2 | 4 | David | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | David | Not yet started | 1
As a worker, I want to list my contact details on the contact us page so I can publish my contact to customers | Design contact info for worker UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert contact info for worker UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create contact info for worker API back-end | 2 | 4 | David | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | David | Not yet started | 1
As an admin, I want to add new worker so all new workers are accounted for | Design add new worker UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert add new worker UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create add new worker API back-end | 2 | 4 | David | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | David | Not yet started | 1
As an admin, I want to edit worker information so that any details can be changed/removed when needed | Design edit worker information UI | 1 | 1 | Rodrigo | Not yet started | 1
| Convert edit worker information UI to front-end code | 1 | 2 | Winston | Not yet started | 1
| Create edit worker information API back-end | 2 | 4 | David | Not yet started | 1
| Perform Unit Test and functionality validation against DoD | 3 | 1 | David | Not yet started | 1